www.agilityio.com

# Nhat Duong - ESTIMATION & ROADMAP BREAKDOWN

26th Jun, 2026

# OVERVIEW

This document provides an estimation and roadmap breakdown for the NestJS Practice — Facebook Creator Platform.

This document defines:

- Scope of work (backend only)

- Task breakdown by module and supporting service

- Timeline & estimation across 20 working days

# TIMELINE

- Total: ~28 working days (≈5.5 weeks) — re-baselined for CR-01

- Working days: 5 days/week × 4 weeks = 20 days (weekends excluded)

- Start Date: 29th Jun, 2026 (Mon)

- End Date: 24th Jul, 2026 (Fri)

- Team structure: 1 backend developer

- Capacity: ~6 productive hours/day → ~120h total budget

# TARGET

## Backend

- NestJS (modular monolith — apps/api)

- TypeScript

- Fastify adapter

- MikroORM (Unit of Work, Identity Map)

- MongoDB (Audit Service — schemaless audit trail)

- PostgreSQL (core/billing/analytics schemas)

- RabbitMQ — AMQP (event bus)

- Redis (cache only — permissions, plans, FB metadata)

- Algolia (search indexing)

- Stripe (subscription billing)

- Clerk (authentication)

- Slack API + Email provider (notifications / transactional email)

- Docker / Docker Compose, GitHub Actions, Swagger, Pino

- Artillery (design API testing, Load test)

Note: Frontend is out of scope for this estimation — backend only.

# SCOPE

## In Scope (Backend)

- Monorepo + architecture foundation (apps/api, supporting services, shared libs)

- Identity module (Clerk JWT, RBAC: Owner / Editor / Viewer)

- Workspace module (multi-tenant, members, invitations)

- Facebook module (OAuth, Page connection, token refresh)

- Posts module (CRUD, scheduling, publish state machine)

- RabbitMQ event infrastructure (publisher confirms, retry, DLQ)

- Billing Service (Stripe, subscription state machine, plan enforcement)

- Analytics Service (Graph API metrics sync, aggregations)

- Search Service (Algolia indexing via events)

- Notification Service (in-app + Slack)

- Email Service (transactional email)

- Caching, observability, testing, ADRs, documentation

- E2E to testing API

## Out of Scope

- Frontend / Web UI (Next.js)

- Multi-platform

- AI content generation

- Mobile applications

- Multi-region deployment

# TASK BREAKDOWN (BY MODULES)

## Foundation & Infrastructure

| Task | Description | Estimation | Actual | Status |
| --- | --- | --- | --- | --- |
| Monorepo setup | NestJS monorepo, pnpm, shared libs (contracts, logger, database) | 4h |  | Not Started |
| Docker compose | PostgreSQL + RabbitMQ + Redis local stack | 3h |  | Not Started |
| Config & env | Config module, env validation, health checks | 2h |  | Not Started |
| Base CI | GitHub Actions: lint, build, test | 3h |  | Not Started |
| Result + error model | Result type + AppError taxonomy + Nest exception/Result adapter | 4h |  | Not Started |

Subtotal: 16h

## Identity Module

| Task | Description | Estimation | Actual | Status |
| --- | --- | --- | --- | --- |
| Clerk setup | Integrate Clerk JWT verification | 2h |  | Not Started |
| Auth guard | Verify JWT + attach user context | 3h |  | Not Started |
| RBAC guard | Workspace roles: Owner / Editor / Viewer | 3h |  | Not Started |
| User entity | Create DB model (core schema) | 2h |  | Not Started |
| Identity service & API | getOrCreateUser, GET /auth/me | 3h |  | Not Started |

Subtotal: 13h

## Workspace Module

| Task | Description | Estimation | Actual | Status |
| --- | --- | --- | --- | --- |
| Workspace entity | Multi-tenant DB schema + membership | 3h |  | Not Started |
| Workspace service | Create workspace, resolve role | 4h |  | Not Started |
| Members & invitations | Invite by email, role assignment | 4h |  | Not Started |
| Workspace API | CRUD + members endpoints | 3h |  | Not Started |
| Emit events | WorkspaceCreated, WorkspaceMemberInvited | 2h |  | Not Started |

Subtotal: 16h

## Facebook Module

| Task | Description | Estimation | Actual | Status |
| --- | --- | --- | --- | --- |
| OAuth URL | Generate Facebook login URL | 2h |  | Not Started |
| Callback handler | Exchange auth code for Page token | 4h |  | Not Started |
| Save pages | Store connected Pages + token metadata | 3h |  | Not Started |
| Token refresh | Refresh workflow + TokenExpired event | 3h |  | Not Started |
| Facebook API service | Publish + metrics fetch wrappers | 4h |  | Not Started |

Subtotal: 16h

## Posts Module

| Task | Description | Estimation | Actual | Status |
| --- | --- | --- | --- | --- |
| Post entity | DB schema (status, scheduledAt) | 2h |  | Not Started |
| Post repository | CRUD methods (MikroORM repository) | 3h |  | Not Started |
| Post service | Business logic + plan-quota check | 5h |  | Not Started |
| Status state machine | Draft → Scheduled → Published ¦ Failed | 4h |  | Not Started |
| Post API | Endpoints + status transition | 4h |  | Not Started |
| Emit events | PostCreated, PostPublished, PublishFailed | 2h |  | Not Started |

Subtotal: 20h

## RabbitMQ Event Infrastructure

| Task | Description | Estimation | Actual | Status |
| --- | --- | --- | --- | --- |
| RabbitMQ module | Connection, topic exchange, shared lib | 3h |  | Not Started |
| Publisher | Domain-event publisher + publisher confirms | 3h |  | Not Started |
| Consumer base | Idempotent, manual-ack consumer abstraction | 4h |  | Not Started |
| Retry & DLQ | Retry queues, dead-letter queue, dedup | 3h |  | Not Started |

Subtotal: 13h

## Billing Service

| Task | Description | Estimation | Actual | Status |
| --- | --- | --- | --- | --- |
| Plan entity | Free / Pro / Team plans | 2h |  | Not Started |
| Subscription entity | DB schema (billing schema) | 3h |  | Not Started |
| Stripe checkout | Create checkout session | 4h |  | Not Started |
| Webhook handler | Signature verify + handle events | 4h |  | Not Started |
| Subscription state machine | Trial → Active → Past_Due → Cancelled (guarded transitions + state diagram + transition log via billing_events) | 4h |  | Not Started |
| Plan guard | Enforce plan limits in apps/api | 3h |  | Not Started |

Subtotal: 24h

## Analytics Service

| Task | Description | Estimation | Actual | Status |
| --- | --- | --- | --- | --- |
| Metrics entity | DB schema (analytics schema) | 2h |  | Not Started |
| Consumer | Consume PostPublished → schedule sync | 3h |  | Not Started |
| Analytics service | Graph API fetch + store aggregates | 5h |  | Not Started |
| Analytics API | Post + workspace overview endpoints | 3h |  | Not Started |

Subtotal: 13h

## Search Service

| Task | Description | Estimation | Actual | Status |
| --- | --- | --- | --- | --- |
| Algolia setup | Index config + SDK integration | 2h |  | Not Started |
| Index consumer | Consume PostCreated/Published → index | 4h |  | Not Started |
| Search query | Full-text search wiring for posts list | 3h |  | Not Started |

Subtotal: 9h

## Notification Service

| Task | Description | Estimation | Actual | Status |
| --- | --- | --- | --- | --- |
| Notification entity | In-app notification DB schema | 2h |  | Not Started |
| Notification consumer | Consume events → in-app notifications | 3h |  | Not Started |
| Slack alerts | Operational alerts via Slack API | 2h |  | Not Started |

Subtotal: 7h

## Email Service

| Task | Description | Estimation | Actual | Status |
| --- | --- | --- | --- | --- |
| Email service | Provider integration + templates | 3h |  | Not Started |
| Email consumer | Invitations, publish result, subscription, token | 4h |  | Not Started |

Subtotal: 7h

## Audit Service

| Task | Description | Estimation | Actual | Status |
| --- | --- | --- | --- | --- |
| Mongo setup | MongoDB driver + Docker compose service | 2h |  | Not Started |
| Audit consumer | Consume all domain events → append audit doc | 4h |  | Not Started |
| Audit query API | Read endpoints (per workspace / entity) | 3h |  | Not Started |

Subtotal: 9h

## Cross-Cutting: Testing, Docs & ADRs

| Task | Description | Estimation | Actual | Status |
| --- | --- | --- | --- | --- |
| Unit tests | Jest across modules/services | 6h |  | Not Started |
| API tests | Artillery smoke + Supertest for apps/api endpoints | 4h |  | Not Started |
| Swagger docs | OpenAPI spec + decorators | 3h |  | Not Started |
| ADRs | Complete 10 architecture decision records | 3h |  | Not Started |
| Hardening/buffer | Bug fixing, integration polish | 4h |  | Not Started |
| Load test | Load test design & runs (Artillery) | 6h |  | Not Started |

Subtotal: 26h

## Estimation Summary

| Area | Estimation |
| --- | --- |
| Foundation & Infrastructure | 16h |
| Persistence migration (MikroORM) | 10h |
| PII & encryption | 8h |
| App-generated keys + soft delete + timestamps | 11h |
| Identity Module | 13h |
| Workspace Module | 16h |
| Facebook Module | 16h |
| Posts Module | 20h |
| RabbitMQ Event Infrastructure | 13h |
| Billing Service | 24h |
| Analytics Service | 13h |
| Search Service | 9h |
| Notification Service | 7h |
| Email Service | 7h |
| Audit Service (MongoDB) | 9h |
| Testing, Docs & ADRs | 26h |
| FK index pass | 2h |
| Total (gross) | ~222h |
| Working budget (20 days × ~6h) | ~120h |

Gross estimate re-baselined to ~222h for CR-01 (was 166h): +56h for MikroORM migration, PII encryption, application-generated keys, soft-delete timestamps, the Result pattern, the MongoDB Audit Service, the billing state machine, FK indexing, and Artillery load testing. This no longer fits the original 120h budget; the timeline is extended to ~28 working days. Scope is prioritised so the foundation (MikroORM, BaseEntity with uuid v7 + timestamps + soft delete, PII encryption, Result pattern) is in place from Week 1, before any feature code. Core modules and Billing follow; the Audit Service lands in Week 3 once the event bus is stable; Search/Notification/Email in Week 4; hardening, verification and Artillery load testing close out Week 5.

# TIMELINE (28 WORKING DAYS)

## Week 1 — Foundation + Core Domains

| Day | Task | Status |
| --- | --- | --- |
| Day 1 | Monorepo (pnpm), Docker compose (PostgreSQL + MongoDB + RabbitMQ + Redis), config, CI | Not Started |
| Day 2 | Foundation — MikroORM (UoW) + BaseEntity (uuid v7, created/updated/deleted_at, soft-delete), EncryptedText (PII), Result/AppError + HTTP mapper | Not Started |
| Day 3 | Identity module — Clerk JWT, auth guard, RBAC guard, user entity | Not Started |
| Day 4 | Workspace module — entity, service, role resolution | Not Started |
| Day 5 | Workspace module — members & invitations, API, emit events | Not Started |

## Week 2 — Facebook + Posts + Event Bus

| Day | Task | Status |
| --- | --- | --- |
| Day 6 | Facebook module — OAuth URL, callback, save pages (token encrypted via EncryptedText from first write) | Not Started |
| Day 7 | Facebook module — token refresh, Facebook API service | Not Started |
| Day 8 | Posts module — entity, repository, service + plan-quota check; status state machine | Not Started |
| Day 9 | RabbitMQ infra — connection, topic exchange, publish-after-commit confirms | Not Started |
| Day 10 | RabbitMQ infra — idempotent consumer base, retry queues, DLQ, dedup; testing | Not Started |

## Week 3 — Billing + Analytics

| Day | Task | Status |
| --- | --- | --- |
| Day 11 | Billing — plan & subscription entities (app-gen ids), Stripe checkout | Not Started |
| Day 12 | Billing — webhook handler, guarded subscription state machine + transition log | Not Started |
| Day 13 | Analytics — metrics entity (logical postId, indexed), consumer, Graph API sync | Not Started |
| Day 14 | Audit Service — MongoDB setup, consume every event, append-only trail | Not Started |
| Day 15 | Audit read API (apps/api, Owner-only) + Analytics API; testing | Not Started |

## Week 4 — Search, Notifications, Email

| Day | Task | Status |
| --- | --- | --- |
| Day 16 | Search Service — Algolia setup, index consumer, search query | Not Started |
| Day 17 | Notification Service — in-app + Slack (one-way read status) | Not Started |
| Day 18 | Email Service — consumers (invitation, publish, subscription, token); dedupe_key | Not Started |
| Day 19 | Cross-cutting — unit + API tests, Swagger docs, ADRs | Not Started |
| Day 20 | Buffer — bug fixing, integration polish, end-to-end review | Not Started |

## Week 5 — Hardening, Verification & Load Testing

| Day | Task | Status |
| --- | --- | --- |
| Day 21 | MikroORM/UoW verification pass — full migration matches fcp-ddl.sql; soft-delete filter global | Not Started |
| Day 22 | Schema audit — no DB id defaults on service tables; every table has the timestamp triplet | Not Started |
| Day 23 | PII verification — tokens encrypted at rest; logs/events carry no PII (integration grep) | Not Started |
| Day 24 | Result-pattern + FK-index pass — no domain throw in services; every FK (real+logical) indexed | Not Started |
| Day 25 | Artillery — API smoke + load scenarios vs capacity targets (read p99 < 300ms, write p99 < 500ms) | Not Started |
| Day 26 | Artillery — publish fan-out (no DLQ growth) + auth/RBAC cache-first; save reports | Not Started |
| Day 27 | Load-test fixes — address regressions found; tune indexes/caching | Not Started |
| Day 28 | Buffer — final review, docs sync, demo prep | Not Started |

# NOTES & ASSUMPTIONS

- Estimation counts working days only (Mon–Fri); weekends and holidays are excluded.

- One backend developer at ~6 productive hours/day; the remaining time covers reviews, meetings, and context switching.

- Supporting services share a single PostgreSQL instance via dedicated schemas; the Audit Service uses a separate MongoDB instance (schemaless), provisioned via Docker Compose (CR-01 R6).

- Days 20 and 28 are explicit buffers; if earlier days slip, lower-priority items (extra tests, Notification and Email polish, load-test tuning) flex first.

- Frontend integration is out of scope; API contracts are documented via Swagger for a future FE effort.

# CHANGE LOG

| Version | Date | Notes |
| --- | --- | --- |
| v1.0.0 | 2026-06-26 | Initial backend-only estimation & roadmap (4 weeks / 20 working days). |
| v1.1.0 | 2026-06-29 | CR-01: MikroORM, PII encryption, app-generated keys, soft-delete timestamps, Result pattern, MongoDB audit service, billing state machine, FK indexing, Artillery load testing. Re-baselined 166h → ~222h. |